# Internship Workflow Guide — 2nd Year Batch (B.Tech CSE-AIDE)

Duration: 22 June 2026 → 26 July 2026 (5 weeks, ~25 working days) Mode: Individual work. No teams. No group projects. Outcome: 1 shippable project + 1 mini-extension + 1 written reflection, all building a foundation for 3rd year placements.

## 1. The Big Picture

You are NOT here to do a placement-ready, interview-defensible, production-grade system. Not yet. You have one more year before placements — that year is where the production-grade work happens.

You ARE here to do three things:

| What | Why |
| --- | --- |
| Build a real, working, deployed thing end-to-end | Prove to yourself you can. This is the foundation of 3rd year. |
| Get a working command of the core tools in your chosen track | The 3rd year internship will assume you know these. If you don't know them now, you'll drown later. |
| Walk away with a project you can keep building | Your 3rd year portfolio starts here. You will extend this project — not start a new one. |

The 3rd year internship is for "depth and polish." This one is for "I have the basics down and a real thing to show for it." Different game. Different output.

## 2. The 4 Segments (Pick ONE)

The 4 segments are deliberately broader than the 3rd year ones. We're not yet asking you to pick a niche like "MLOps" or "LLMOps" — you're picking a track you'll be in for the next 18 months.

| # | Segment Name | What you'll be ready to do in 3rd year | Target roles (after 3rd year) |
| --- | --- | --- | --- |
| 1 | Foundations of Analytics Engineering | SQL fluently, dashboard built, warehouse modelled, data story told | Data Analyst · BI Analyst · Junior BA · Analytics Consultant |
| 2 | Foundations of Data Engineering | Pipeline built, containerised, deployed, with tests and a README | Data Engineer · Analytics Engineer · Junior DE |
| 3 | Foundations of Applied Machine Learning | Model trained, evaluated, deployed, with a frontend the user can poke | ML Engineer · AI Engineer · Junior Data Scientist |
| 4 | Foundations of Cloud & DevOps | App deployed, CI/CD set up, infrastructure-as-code, monitored | Cloud Engineer · DevOps Engineer · SRE · Platform Engineer |

Rule: Pick the segment that matches what you want to be doing daily in 3rd year and beyond. If you're torn between two, pick the one with steeper industry demand for your target city, not the one your friend picked.

## 3. The Problem Statements (Pick ONE within your segment)

You will find the full catalogue in Document 02: Technical & Business Problem Compendium.

Quick map:

Segment 1 — Foundations of Analytics Engineering

- G1. Student Performance Twin — Build a personal analytics dashboard from your own academic data

- G2. CampusOps 360 — Analytics for a real campus operation (mess, hostel, transport, library)

- G3. LocalBiz Insights — Partner with a real local business, build KPIs from their data

Segment 2 — Foundations of Data Engineering

- H1. APIs to Warehouse — Ingest a public API → warehouse → BI tool, end-to-end

- H2. CSV Hell Pipeline — Handle 5 dirty, differently-shaped daily CSV drops into a clean warehouse

- H3. Real-time Hashtag Pulse — Stream public data → Kafka → Spark → live dashboard

Segment 3 — Foundations of Applied ML

- I1. Tabular ML Zoo — Kaggle-style problem, full lifecycle, end-to-end app

- I2. Document Q&A — RAG over a focused corpus (your textbook, a research area, college docs)

- I3. Vision Starter — Image classification / detection on a focused dataset, deployed

Segment 4 — Foundations of Cloud & DevOps

- J1. Portfolio-as-a-Service — Your own site, deployed, CI/CD, monitored

- J2. Internal Tool Backbone — A small but real internal tool (issue tracker, leave manager, club signup)

- J3. API Gateway & Rate Limiter — Kong/Traefik in front of public APIs with rate limiting and dashboards

## 4. The 5-Week Workflow

This is intentionally slower-paced than the 3rd year internship. You have more learning time, more mentor touchpoints, and more forgiving deadlines. Use the time to actually understand what you're doing — don't rush to ship.

### Pre-Internship (Before 22 June)

- Read this workflow guide fully.

- Skim the Technical & Business Problem Compendium.

- Identify your top 2 segments and top 3 problem statements.

- Set up: GitHub account (clean profile), Python 3.11+, Git, a code editor.

- Optional but recommended: Docker, a free-tier cloud account.

- Join the cohort Slack/Discord.

- Pre-work assignment (released 18 June, due 21 June): complete a 2-hour Python + Git refresher exercise. Not graded, but missing it sets you back.

### Day 1 (22 June, Mon) — Segment Orientation

- Morning: Welcome + segment overviews by mentors.

- Afternoon: Self-assessment + Segment Ranker form (skills, interests, target city, target role).

- Evening: Problem-statement teasers released. Mentors host 30-min open Q&A in their segment.

### Day 2 (23 June, Tue) — Problem Deep-Dive

- Per-segment deep-dives (scenario, scope, what you'll learn, what you'll ship).

- 1:1 with your segment mentor (15 min, sign up via form).

### Day 3 (24 June, Wed) — Lock Your Choice

- Submit your final segment + problem statement.

- Submit your 1-page Design Doc by 11:59 PM (template provided). Don't worry about getting it perfect — mentor will iterate with you.

### Day 4-5 (25-26 June, Thu-Fri) — Setup + Architecture Review

- Day 4: 1:1 with mentor to walk through the design doc. Get sign-off on tech stack.

- Day 5: Repo created, environment set up, data exploration started. First commit pushed.

- Friday EOD: Architecture + tech stack signed off by mentor.

### Week 1 (29 Jun – 3 Jul) — Learn + Build Foundation

Theme: Set up the bones. Get the data layer working. Spend at least 30% of the week learning the tools, not just using them.

- Set up: repo, virtual env / Docker, data sources, basic tooling.

- Build: the data layer (ingestion, warehouse, dataset — whatever applies).

- Learning target this week: be able to explain in your own words: "what does this tool do, why did I pick it, and what would break if I removed it."

- Friday demo #1: Show the data flowing + a short explanation (3 min) of your tech stack choices.

### Week 2 (6 Jul – 10 Jul) — Core Build + Mid-Point Check-in

Theme: The "skinny" version of the product works end-to-end.

- Build: the core model / pipeline / dashboard / deployment.

- Learning target: document each technical decision in a short note (1 paragraph per decision). This is the start of your ADRs.

- Friday demo #2: End-to-end demo (5 min). Ugly is fine. Working is the bar.

- Mid-program 1:1 with mentor (Wed of this week). 30 min. Review progress, unblock, recalibrate if needed.

### Week 3 (13 Jul – 17 Jul) — Polish + Mini-Extension

Theme: Make it presentable. Add the mini-extension (a small, scoped addition that shows you can go beyond the minimum).

- Add: tests (1-2 are enough, just show you can), README polish, a simple "About" page.

- Build the mini-extension (see Doc 02 for what this looks like for your problem).

- Learning target: be able to onboard a friend to your repo in 15 minutes.

- Friday demo #3: Polished version of the product + the mini-extension demoed.

### Week 4 (20 Jul – 24 Jul) — Deploy + Document

Theme: Get it on the public internet. Write it up.

- Deploy: live URL on a free-tier cloud (or local + public tunnel).

- Write: README final, ADR set (3 ADRs minimum), a 3-min Loom walkthrough.

- Write: your reflection piece (the 1 written deliverable, see Doc 02 for spec).

- Friday demo #4: Live deployment demo + walkthrough.

### Week 5 (25-26 Jul) — Final Submission & Showcase

- 25 Jul (Sat): Final submission (repo, deployed URL, README, Loom, reflection, resume bullets). Internal review.

- 26 Jul (Sun): Public showcase. All students present (5 min each, segment-grouped). Certificates issued.

## 5. The 3-Output Rule

Every student ships exactly 3 outputs by 26 July:

| # | Output | What it is | Why it matters |
| --- | --- | --- | --- |
| 1 | The Hero Project | The working, deployed, documented project tied to your problem statement | Foundation of your 3rd year portfolio |
| 2 | The Mini-Extension | A small, scoped addition that goes beyond the minimum | Shows you can go deeper, not just wider |
| 3 | The Reflection | A 1000-1500 word written piece on what you learned, what you'd do differently, what to learn next | Trains the writing muscle + gives the next-internship team signal |

The mini-extension is what makes the 2nd year internship different from a 3rd year one. In the 3rd year, you'd ship 2-3 separate projects. Here, you ship 1 project + 1 well-scoped extension. The extension is what shows you can go beyond "I did the assignment."

Examples of good mini-extensions (you'll see the specific one for your problem in Doc 02):

- The Analytics project gets a "what-if simulator" added to the dashboard

- The DE project gets a streaming source added to the batch pipeline

- The ML project gets an A/B test comparison view added

- The DevOps project gets a chaos test added to the deployment

## 6. Weekly Cadence (The Rhythm)

| Day | Activity |
| --- | --- |
| Monday | Sprint planning: 3-5 tasks for the week in a GitHub Project board. |
| Tue–Thu | Build. Commit at least 3 times. Push. |
| Friday | Demo day. 3-5 min walkthrough. Get feedback. Record. |
| Saturday | Write: README updates, ADR drafts, learning notes, blog draft. |
| Sunday | Off. Rest. Read. Catch up. |

Push code often. A green commit graph in your GitHub profile is itself an artifact.

## 7. The "Push Every Day" Pledge

This is the single biggest differentiator between students who walk out of this internship ready for 3rd year and students who don't. Make a pledge to yourself: commit and push something to your GitHub every day, even if it's just a README update or a one-line fix. By 26 July, you'll have 30+ commits. That graph becomes a story: "this person works consistently." Recruiters read it.

## 8. What "Done" Looks Like at 2nd-Year Level

A done 2nd year project has:

- ✅ Code in Git, with regular commits

- ✅ README that explains the why, what, how, and how-to-run

- ✅ A deployed, live URL (free-tier is the standard)

- ✅ At least 1 test (a passing test is enough — you're learning the discipline)

- ✅ A 3-min Loom showing it working

- ✅ A reflection piece (1 written output)

- ✅ A clear path to extend it in 3rd year

It does NOT need:

- ❌ Multiple models compared

- ❌ A full eval harness

- ❌ ADRs for every decision

- ❌ A blog post

- ❌ Tests on every function

- ❌ A CI/CD pipeline (basic GitHub Actions deploy is enough)

Know the difference. This is the foundation. 3rd year is the production polish.

## 9. Mentorship — How It Works Here

The 2nd year batch gets more mentor attention than the 3rd year batch. Specifically:

- 1 mentor per 8-10 students (vs 1:15+ for 3rd year)

- Weekly 1:1 with your mentor (scheduled Mon-Fri, 15 min). Non-negotiable.

- Open office hours every Wed + Fri, 4-6 PM. Walk in, no appointment.

- Pair-debug sessions if multiple students are stuck on similar issues (mentor will arrange).

- Slack #help channel monitored daily by at least 1 mentor.

You are expected to use this. A 2nd year student who finishes the internship without having had at least 4 mentor 1:1s is doing it wrong.

## 10. Help & Escalation

| Need | Where to go |
| --- | --- |
| Stuck on a concept | Segment mentor in 1:1, or office hours |
| Stuck on a build issue | Cohort Slack #help channel |
| Personal blocker | Internship coordinator — no judgement, no questions |
| Disagreement with mentor | Raise to internship lead, 24-hr turnaround |
| Want to switch problem statement | Allowed only in Week 1, with mentor sign-off |
| Failing behind, overwhelmed | Tell your mentor by Wednesday of Week 2. Don't hide. We will scope down or extend. |

## 11. What's NOT Allowed

- ❌ Group projects of any size

- ❌ Submitting work done before 22 June 2026

- ❌ Submitting a closed-source project

- ❌ "I couldn't deploy it" — there is a free tier for every cloud

- ❌ Skipping the reflection piece

- ❌ Going silent. If you're stuck, say so within 24 hours of being stuck

- ❌ Copy-pasting tutorials. The data, the analysis, the decisions must be yours

## 12. The Final Eval

You will be evaluated on 4 dimensions, each equally weighted:

- Working Software (30%) — Does it work? Is it deployed? Is it documented?

- Learning Depth (25%) — Can you explain what you built and why? ADRs, design doc, mentor 1:1 conversations.

- Mini-Extension Quality (20%) — Did you go beyond the minimum in a thoughtful way?

- Communication (25%) — README quality, Loom, reflection piece, demo ability, resume bullets.

A clean, working, well-explained project with a thoughtful mini-extension will outscore a half-broken ambitious project. Don't overscope.

## 13. Beyond 26 July — The Extension Path

The point of this internship is what happens after. Each problem statement in Doc 02 has a "3rd Year Extension Path" section. This is your roadmap.

For example:

- Analytics student extends by adding a predictive churn model on top of the dashboard

- DE student extends by adding streaming, then by adding data contracts, then by adding a feature store

- ML student extends by adding a continuous-training loop, then by adding a feature store, then by adding a proper eval harness

- DevOps student extends by adding multi-tenancy, then by adding chaos engineering, then by adding a service mesh

By the time 3rd year internship rolls around, you should be extending the project you started here, not starting from zero. The 3rd year internship's "ship 3 artifacts" bar is much higher because you're standing on this foundation.

## 14. Documents in This Series

| Doc | Purpose |
| --- | --- |
| 01 — Workflow Guide (this doc) | What to do, when, how. Process. |
| 02 — Technical & Business Problem Compendium | Detailed scenarios, scope, tech direction for every problem statement + the 3rd year extension path. |
| 03 — Deliverables Specification | Exact weekly + milestone + final deliverables, format, evaluation. |

Read 01 fully before 22 June. Start skimming 02 by 20 June. Read 03 fully by 24 June.

One last thing. 2nd year internship is the easiest internship you'll ever do — in the sense that the bar is "real, working, deployed, with a reflection piece." 3rd year internship will demand 2-3 projects. After placements, the bar goes up again. Don't peak too early. Use this month to build the foundation, the habits, and the confidence. The 3rd year internship will reward that.

See you on 22 June.